## Tasks
Sr.No | Issue/Item | Type | Accountability | Priority | Timeline in HRS | Date Added | Estimated delivery | Date Completed | Gateway Analysis | Status | Gateway Comments | HRQ Comments
1 | S1 Library - Employer purchase Hazard - check out window missing XP icons. Shopping cart confirming missing image | Glitch | HRQ | [6 empty] | Done | Please explain in detail and with specific example
2 | S1 Inspections - Can’t select inspections to add to Drag and Drop - Can’t check out using credits | Glitch | Gateway |  | - |  |  |  |  | Ignore it here, will be explained in other item below | aug-31-2015 [Kartik]: Not allowing links are not drag & drop on the customised panel else all other tiles are drag & drop
3 | Can only buy one inspection at a time (Multiple inspection function (drag and drop - not working)) | Glitch | Gateway |  | - |  |  |  |  | Ignore it here, will be explained in other item below | aug-31-2015 [Kartik]: Needs to implement
4 | Once purchased content overlaps in the modal | Glitch | Gateway |  | - |  |  |  |  | Ignore it here, will be explained in other item below | aug-31-2015 [Kartik]: Please explain in detail and with specific example
5 | My H&S Program - Inspections Grouped/purchased don’t show | Glitch | Gateway |  | - |  |  |  |  | Ignore it here, will be explained in other item below | aug-31-2015 [Kartik]: Enhancement
6 | My H&S Program -Procedures - Displays multiple new procedures - should only show “New procedure” | Enhancement | Gateway | 1 | 5 | aug-31-2015 |  | oct-21-2015 | Enhancement | Done | aug-31-2015 [Kartik]: Not a Glitch. "New Procedure" are the default name after purchase. You could change from the "Purpose" Modal | Do the inventory if user buys more than one “new Procedure”, once he opens and save first field, it should go as a new tile and decrease the inventory number in its badge.
7 | New Procedures - Some boxes are already green | Glitch | Gateway |  | 4 | aug-31-2015 |  | sep-05-2015 | Glitch | Done | aug-31-2015 [Kartik]: Not a Glitch. Please let me know which style you want to change in this scenario | Select box green, for new procedure, tiles has been already selected in green, even for the first time opened. We expected the green border only after user accessed and save each section.
8 | 1 (title and Purpose) does not show message indicating “Saved Data” | Glitch | Gateway |  | 3 | aug-31-2015 |  | sep-04-2015 | Change Request | Done | aug-31-2015 [Kartik]: Ok we will update sep-01-2015: CHANGE REQUEST | Implement standard modal: “Your information has been saved”, in all tiles under procedures, once they are saved.
9 | Risk Rating Hazards - Descriptions missing Scroll over icons don’t work properly appear to be see threw | Enhancement | HRQ |  |  |  |  | Sep-08-2015 |  | Done | Not a Glitch. We are showing only title so far. Now as per the request we will add description | Insert descriptions provided to each risk rating. Tooltip over second line of tiles does not show clearly the text, put it darker.
10 | New Procedure - Kicked user out of system (3) - went back in and ok | Glitch | Gateway |  | 3 | aug-31-2015 |  | sep-04-2015 | Glitch | Done | aug-31-2015 [Kartik]: Please explain in detail and with specific example | While inserting content in a "procedure", system logged out, similar to what happened few months ago.
11 | Select Training -(remove fall protection from training list) | Duplication - correction | HRQ | [6 empty] | Done | We have not found any duplication, Could you please explain with specific example if anything. | Training modal: SWITCH “Trainings” to “Training”. Replace “Fall Protection” to “Work at Heights”
12 | Button 5 - Equipment & add text/copy/paste to Manufacturer’s Instructions | Enhancement | OBSOLETE | [6 empty] | OBSOLETE | Ok.
177 | ADMIN DATA COLLECTION - implement scripts | Enhancement | Gateway | 1 | 44+24 | Sep-19-2015 |  |  | Enhancement | In progress | oct-31-2015 [Kartik]: 44Hrs = 36hrs Development efforts + 8hrs HTML efforts nov-25-2015 [Kartik]: http://mys1s.ca/admin/my_data_collection?design=1: Done http://mys1s.ca/admin/union_admin_data_collection?id=135: Done http://mys1s.ca/admin/purchases_admin_data_collection: Done(100%) [Remaining Graph section has been done too]. @Phillip, I have put the Item177 on hold and would resume after our scheduled Teleconference for the Data Collection, on Wednesday, 12 PM (Canada Time). [Kartik] - Additional comments mentioned in "Item comments" TAB | [Sep-21-2015] Still under analysis from my side, tomorrow I'll finish and give you respective direction. [Oct-02-2015] Third part company will implement standard header and footer into new scripts. [Oct-29-2015] Third part company already implemented solution as per S1 team request. See email sent today. I got the scripts and upload to our server at httpdocs/mys1.
13.2 | PROCEDURE - DUE DILIGENCE - Regulation main dropdown list | Enhancement | Gateway |  | 1 | aug-31-2015 |  | oct-02-2015 | Enhancement | Done |  | Actually we have only regulation number, we should add their titles beside.
14 | Risk Rating does show coloured slider/bar - Under preview it is not working the collapsed item. | Glitch | Gateway | 1 | 7+4 | aug-31-2015 |  |  | Glitch |  | aug-31-2015 [Kartik]: Not a Glitch. Let me know if you want to remove color or update color in the same. sep-25-2015: Done(70%), found the conflicts in plugins, merging and removing few conflicted scripts dec-22-2015 [Kartik]: This has been resolved on the preview modal of those procedures which are saved&closed. Now as per I tested more research required to fix conflictions of modal on the procedures which are not saved&closed. | Under preview it is not working the collapsed item. [Sep-02-2015] Kartik, once you get this item, please check all collapsible sections to make sure they are working. [Sep-08-2015] Kartik, under preview, the progress bars are not showing the previous selection of colours, it opens with the right values on top, but progress bar in the left position. Could you check it please? [Sep-18-2015] Kartik, it is still not working, check procedure id=176, Risk Rating progress bar works good on the proper modal section, but it is not working the same way under Preview Modal.
15 | Purpose - needs to say “Title”, date created looks weird , need to add Purpose | Enhancement | HRQ |  |  |  |  | Sep-08-2015 |  | Done | Ok we will resolve | Redesign title and date to be similar to modal.
16 | Risk Rating - Bars should not be moveable in preview mode | Glitch | OBSOLETE | [6 empty] | OBSOLETE | Ok we will resolve
17 | Procedures - Tips are not showing in preview and order reversed | Glitch | Gateway |  | 1 | aug-31-2015 |  | sep-02-2015 | Glitch | Done | aug-31-2015 [Kartik]: Ok we will check the same sep-02-2015 [Kartik]: This has been done | Tips are not showing in preview
17.1 | 17 (a) Procedures need to be itemized the same way as entered | Enhancement | HRQ | [6 empty] | Done | Please explain in detail and with specific example | Remove number on modal, and insert “place”: Itemize content, ex.: 1. Worker shall wear PPE...”
18.1 | Due Diligence - Preview content - displaying W/S/E | Enhancement | HRQ |  |  |  |  | Sep-02-2015 |  | Done | Ok | S1 will supply content for Worker/Supervisor/Employer tabs
18.2 | PROCEDURES - DUE DILIGENCE | Enhancement | HRQ | [6 empty] | Done |  | Switch from “Regulation Overview” to “Duties and Responsibilities”
179 | UNION DATA COLLECTION - implement scripts | Enhancement | Gateway | 1 | 30+12 | Sep-19-2015 |  |  | Enhancement | In progress | oct-17-2015 [Kartik]: 30Hrs = 22hrs Development efforts + 8hrs HTML efforts [Kartik] - Additional comments mentioned in "Item comments" TAB | [Sep-21-2015] Still under analysis from my side, tomorrow I'll finish and give you respective direction. [Sep-25-2015] Sent e-mail with specs for this task. [Dec-27-2015] Regards your request for clarification about filter Location: Under Courses page, "COURSES" table, filter "location" refers to Union Campus, selected when we created Union Libraries, once Admin selects Union Library Type on field "Type" on http://mys1s.ca/s1dev/admin/new_library, Admin select the campus which this library (course) is applied. Please find attached screenshot.
20 | Glossary - No input available | Glitch | Gateway |  | 2 | aug-31-2015 |  | sep-02-2015 | Change Request | Done | sep-01-2015: CHANGE REQUEST | Remove Glossary from Preview for Users who bought new procedures. Keep it only for Procedures created by S1.
21 | Notifications - at top right of page. Should show modal with appropriate wording -FC, library, H&S program | Enhancement | Gateway | 3 | 4 | aug-31-2015 |  | oct-26-2015 | Enhancement | Done | aug-31-2015 [Kartik]: Not a Glitch | Remove notification and implement modal with: Your Custom Procedure Title: [“title”] Has been saved to your H&S Program. - Once closed, it should send user to his My H&S Program/My Procedures.
22 | Go to Employer - “My workers” - can’t assign content - BIGGEST ISSUE (in any area of the library) | Enhancement | Gateway | 18 | 4 | aug-31-2015 |  | oct-01-2015 | Enhancement | Done | aug-31-2015 [Kartik]: Glitch was related to the "completed library" assigned to user which has been resolved and uploaded on the dev server now. | Implement assign content on My Worker page, make sure messages and notifications are working
23 | Inspections – JHSC and H&s Reps Users - list is populating from “all” system users. Should only populate from “My workers and crews” | Glitch | Gateway |  | 1 | aug-31-2015 |  | sep-02-2015 | Working Fine | Done | aug-31-2015 [Kartik]: Ok we will check the same sep-02-2015 [Kartik]: Rechecking timeline given and it's working fine | JHSC and H&S REPS Users - list is populating from “all” system users. Should only populate from “My Workers”
24 | INSPECTIONS - Go Button at the button of “Workplace” switch to “save” | Enhancement | HRQ |  | 10 |  |  |  |  | Done | Change Request
25 | All type fill boxes should start at the left | Enhancement | Gateway | 13 | 3 | aug-31-2015 |  | oct-02-2015 | Enhancement | Done | aug-31-2015 [Kartik]: Change Request | Implement text field wider, or text area, or text box, with limited numbers of characters (max 100), showing all characters typed.
26 | INSPECTION - Worker Assigned - Select worker(s) and add to empty box beside | To review | HRQ | 31 | 1 |  |  | Sep-13-2015 |  | Done | Ok we will check the same | Once item it is failed, insert content to instruct user to do multiple selections (Ctrl + click). Verify Tablet functionality. Test assigning to my worker item failed.
27 | Inspections - Select (?) Does not show Regulation wording | Gap | HRQ | [6 empty] | Done | Ok we will resolve | Insert content on first modal as “Click on section to view regulation.”
28 | Once Inspection is saved needs to go to “Completed” in “My H&S Program” Inspections did not save - total inventory did not go down | Glitch | Gateway | 1 | 3 | aug-31-2015 |  | sep-11-2015 | Glitch | Done | aug-31-2015 [Kartik]: Ok we will check the same sep-11-2015[Kartik]: We have check that after save inspection, it shows in the "Completed" tab. Now here, Total inventory would be goes down only after any purchased inspection assigned to any user.
29 | Once Inspection is saved -cannot review failed actions and who they were assigned to, whether they were assigned, actions taken | Enhancement | HRQ | 32 | 3 |  |  | Sep-15-2015 |  | Done | Glitch was related to the "completed library" assigned to user which has been resolved and uploaded on the dev server now. | Improve style of message received from Worker for Corrective Action.
30 | Inspections (I) - information - not displaying tutorial for Inspections | Enhancement | S1 | [7 empty] | Ok | S1 will supply content.
31 | Investigations - MOL Officer attended - text box error | Glitch | HRQ | [6 empty] | Done | Ok we will resolve | Cover section, jumping line for MOL Officers...
32 | INVESTIGATION - Detailed description & Incident - text disappears in text box | Glitch | Gateway |  | 1 | aug-31-2015 |  | sep-04-2015 | Change Request | Done | aug-31-2015 [Kartik]: Ok we will resolve sep-02-2015: CHANGE REQUEST. It was set to maintain designs. | Implement text field wider, or text area, or text box, showing all characters typed.
33 | Incident details - select radio boxes - don’t show check work - can’t select multiple items | Glitch | OBSOLETE | [6 empty] | OBSOLETE | Ok we will resolve
212 | S1 LIBRARY - MEDIA BUTTON - display all images related to this library in the carousel. Please see my comments in the proper column. | Enhancement | Gateway | 1 | 2 | Nov-09-2015 |  | nov-18-2015 | Enhancement | Done |  | Kartik, only for the modal coming from MEDIA tile in the bottom of the library view page, please change the script to load all images and videos related in all pages into these carousel. Currently we are loading only the images related to each page, but we need this MEDIA tile with 100% of the images, users will still be able to see related image per page in the right side of the content panel.
35 | INVESTIGATION - Injury Report - Worker 1 info should populate - difficulty entering text | Glitch - System should be smarter than that | Gateway |  | 3 | aug-31-2015 |  | sep-02-2015 | Working Fine | Done | aug-31-2015 [Kartik]: Pending to Review sep-02-2015: Core functionality is working fine, Page reloaded now. | Once user insert injured worker in the first section(Detailed Description of the Incident), system should bring same injured workers on section Injury Report.
36 | INVESTIGATION - Date of Birth - does not work | Glitch | Gateway |  | 2 | aug-31-2015 |  | sep-05-2015 | Change Request | Done | aug-31-2015 [Kartik]: Pending to Review CHANGE REQUEST | Change element to allow users to select year, the current element allow us only to change month by month.
37 | INVESTIGATION - INJURY REPORT - Preferred language - select from total of languages? No drop down list to select preferred language. Type box for “Other” | Gap | Gateway |  | 3 | aug-31-2015 |  | sep-05-2015 | Change Request | Done | aug-31-2015 [Kartik]: For which module ? And please give more detail with specific example. CHANGE REQUEST | Make it as dropdown list from languages in our database, if other, allow user to type the other.
38 | INVESTIGATION - Injured Worker - Where did worker get treatment - radio boxes not easily identifiable should be able to select multiple | Glitch | Gateway |  | 3 | aug-31-2015 |  | sep-03-2015 | Change Request | Done | aug-31-2015 [Kartik]: Pending to Review sep-02-2015: CHANGE REQUEST | Change it to each option in one different row. Check responsiveness on tablets(iPad and others).
39.1 | INVESTIGATION - INJURY REPORT - Is the worker fit for work “Select status of worker” incomplete | Glitch | Gateway |  | 1 | aug-31-2015 |  | sep-02-2015 | Change Request | Done | aug-31-2015 [Kartik]: Pending to Review sep-02-2015: CHANGE REQUEST | Radio box options in different rows.
39.2 | INVESTIGATION - INJURY REPORT - Is the worker fit for work “Select status of worker” incomplete | Glitch | HRQ | [6 empty] | Done | Pending to Review | Label “Select the Status of the work...” is not well displayed, should be same applied to titles.
40 | INVESTIGATION - INJURY REPORT - How many days was the worker away from work -(Question drop down or improve type box) | Enhancement | Gateway | 35 | 3 | aug-31-2015 |  | oct-01-2015 | Enhancement | Done | aug-31-2015 [Kartik]: Ok | Switch regular text field to a drop down with numbers from 1 to 999.
41 | INVESTIGATION - INJURY REPORT - Injured worker fields should all show | Glitch - System should be smart enough to auto fill injured worker fields | Gateway |  | 3 | aug-31-2015 |  | sep-02-2015 | Repeated with Item35 | Done | aug-31-2015 [Kartik]: Pending to Review. REPEATED | Same to item 35 above
42 | INVESTIGATION - Witness Report - text box should show all information inputted | Glitch | Gateway |  | 2 | aug-31-2015 |  | sep-04-2015 | Change Request | Done | aug-31-2015 [Kartik]: Ok we will resolve sep-02-2015: We have implemented as per the designs | Implement text field wider, or text area, or text box, showing all characters typed.
43 | INVESTIGATION - Material & Equipment section - All text box style does not work | Glitch | Gateway |  | 2 | aug-31-2015 |  | sep-04-2015 | Change Request | Done | aug-31-2015 [Kartik]: Pending to Review sep-02-2015: We have implemented as per the designs | Same as above item 42
44 | Add N/A to section if they do not apply | Repeat | OBSOLETE | [6 empty] | OBSOLETE | Pending to Review
45 | INVESTIGATION - Recommended Corrective Actions: nothing works in this section - assign to who? | Glitch | Gateway |  | 2 | aug-31-2015 |  | sep-02-2015 | Working Fine | Done | aug-31-2015 [Kartik]: Pending to Review 02-sep-2015 [Kartik]: I have send new recommended corrective action from s1 employer to s1 worker on the Live, I got the message in the S1 worker message panel. Please check the messages of the date 02-sep-2015 | Once selected user to corrective action, he didn't get message with corrective action description, sender...
46 | Follow up actions - Where does this data come from? | Review | Gateway |  | 3 | aug-31-2015 |  | sep-07-2015 | Review | Working fine | aug-31-2015 [Kartik]: Pending to Review sep-07-2015 [Kartik] - We have checked and it is working fine | Once item above is working, check if the actual Investigation performer is the right person in this section and if he is able to complete the rest of information.
47 | Photos - I added a photo in machinery and it does not display in this section. Add text to this section - click on thumbnail to enlarge | Glitch | OBSOLETE | [6 empty] | OBSOLETE | Pending to Review | Leave the way it is
48 | UNION LOCAL 183 ICON, remove it on library view and Data Collection pages | Enhancement | HRQ | [6 empty] | Done
173 | H&S PROGRAM - ADMIN LIBRARY - Allow admin to create Training for one specific user Employer or Consultant, which should be able to see on in his own H&S Program page, and assign it to his connections/workers. | Enhancement | Gateway | 2 | 20 | Sep-19-2015 |  |  | Enhancement
50 | INJURIES - Under My Hazards, Injuries Modal, check inconsistency between content and modals. | Review | HRQ | 33 | 1 |  |  | Sep-10-2015 |  | Done |  | Change Labels, switch to Description, Symptoms, Recovery and Stats
51 | 51. S1 LIBRARY, hazards, create relationship to others pieces of libraries as Inspections, Due Diligence, Procedures, Injuries. | Review | HRQ |  | 175 |  |  | Sep-10-2015 |  | Done |  | [Sep-10-2015] Missing only Inspections, results of Phill's decision in our meeting at Sep-09-2015
52 | Landing page - Tools is only opening from cached users | Glitch | HRQ |  |  |  |  | Sep-09-2015 |  | Done |  | [Sep-09-2015] Remove tools button, (put in comments).
53 | Log In - Log in Button and Sign Up Button - Distinguish | Enhancement | HRQ | 22 | 1 |  |  | Sep-13-2015 |  | Done |  | Switch sign up to a button bigger with New User Sign Up!
54 | Duplicate email - Wording | Enhancement | Tulia |  |  |  |  | Sep-02-2015 |  | Done |  | It was finally explained today regarding two email coming from Contact Us page/modal.
55 | Attempted to sign up esfarpa with email Phillip@mys1s.ca - no notification received. Could not proceed with confirmation of registration | Error | HRQ | [6 empty] | Done |  | Remove e-mail sending to marcio@hrqsolution, test other e-mail with domain mys1s.ca
56 | Get Started - need to add languages | Enhancement | Gateway | 1 | 6 | aug-31-2015 |  | oct-07-2015 | Enhancement | Done
57 | Get started - text not aligned | Glitch | HRQ | 1 | 2 |  |  | Sep-10-2015 |  | Done |  | Test in all browsers to check inconsistency not seen in the preliminary testing today [Sep-10-2015] Incompatibility with Chrome browser, should insert class into each parent element with line-height 20pt or higher.
58 | WAT - All modules - Image not same style as other modals | Review | HRQ |  |  |  |  | Sep-02-2015 |  | Done
59 | Content translation picking up font size | Glitch | Gateway | 1 | 4 | aug-31-2015 |  | sep-30-2015 | Glitch | Done | sep-22-2015: Google translation is not translating huge amount of HTML data at once, so I am dividing the data with some limits. Though This issue is not coming in all library the translations, coming in some of library contents. I am checking if I could do with other alternatives. sep-25-2015: Research and Implementation is in progress sep-30-2015: Method updated and working now, please let me know in case if you find any issue while translation | We will check what content is bringing that and provide you the id. [Sep-16-2015] Hrq spent 105m analysing. Now it is Gateway task to be estimated [Sep-17-2015] Kartik, please find library_id 365, HEALTH AND SAFETY AWARENESS TRAINING FOR SUPERVISOR - MODULE 1, paragraph_id = 1149, under paragraph_description field, in the 4th line "Module 1", item "Due Diligence", it comes with html tags in every translation, even if I remove or change it, the html still comes up. Please check if this API has any limitation on the size of string to be translated.
60 | WAT - Inspections, due diligence, injuries (all icon below training) | Incomplete - content emailed to HRQ on August 30th | HRQ |  |  |  |  | Sep-08-2015 |  | Done
61 | WAT - Test start - advise to complete - Insert to content (advice user to start test by clicking on test summary icon below) | Enhancement | HRQ | 34 | 2 |  |  | Sep-19-2015 |  | Done
62 | On Windows - test of SAT/WAT "get summary button" not visible when screen set for 100% becomes visible when set for 75% (zoom). | Glitch | HRQ | [6 empty] | Done |  | Change dynamic height modal to 75%
63 | Windows (modal) pop up window required at the end of module to state you have successfully complete module 1 and click on start next module for module 2 (applies to all) | Enhancement | Gateway | 12 | 3 | aug-31-2015 |  | sep-24-2015 | Enhancement | Done
64 | Module completion - next button does not work 100% - system does not recognize as complete | Glitch | Gateway | 1 | 4 | aug-31-2015 |  | sep-11-2015 | Glitch | Done | sep-09-2015: This has been in the Testing Mode sep-11-2015: This has been done | User should refresh the page to see it working, implement auto refresh in this case
65 | WAT - Module 2 - Question 1 missing response options Question # 7 replace with easier question | Glitch | HRQ |  |  |  |  | Oct-24-2015 |  | Done |  | S1 will supply right information
66 | WAT Modules button does not turn green once complete | Glitch | Gateway |  | 3 | aug-31-2015 |  | sep-08-2015 | Change Request | Done | sep-08-2015: As per we got instruction in Item150 of "Operational Test-Tasks" sheet: Entire "Training" tab would turn Green only if all 8 tiles from WAT and SAT completed. Here you are requesting to turn each module tile Green if that completed though right now module tile is turning Black after completed.
67 | Test on module - Get summary opens new window. If passed when closing summary should close all windows | Enhancement | Gateway | 36 | 2 | aug-31-2015 |  | oct-01-2015 | Enhancement | Done
68 | Home Profile/Info button - 1st slide missing content and also in the "Get Started" | Incomplete | S1 | [8 empty] | S1 will supply right information
69 | WAT - Module sequence screwed up (can access any module in any order) | Glitch | Gateway |  | 3 | aug-31-2015 |  | sep-08-2015 | Glitch | Done
70 | Question 5 - Question doesn't make sense (Module 3) | Incomplete | HRQ |  |  |  |  | Oct-24-2015 |  | Done |  | S1 will supply right information
71 | Once a user completes a test shouldn't be able to access again in "Get Started" (once it's done it's done). | Glitch | Gateway | 1 | 4 | aug-31-2015 |  | sep-11-2015 | Glitch | Done
72 | In My training WAT entire training should display as one training. | Enhancement | Gateway | 1 | 24 | aug-31-2015 |  | oct-18-2015 | Enhancement | Done | sep-01-2015: Not getting exactly. In which modules you want to show WAT and SAT along with points | Worker Awareness Training and Supervisor Awareness Training modules should be displayed as one item each, with the sum of points. [ Sep-02-2015] Kartik, once we created the Awareness training for Worker and Supervisor under Get started page, system should consider these 4 modules as they are only one, with 4 steps to be completed. However we inserted them as 4 pieces of library. So system understand we have 4 different pieces. This request is to display these modules as if they are only one on My HS Program and S1 Library. They were created as Library type "Training", however I think they should be a different Library type (maybe "Awareness Training"), and you could implement logic type for Worker and Supervisor...
73 | Module 1 completed including test and system did not recognize completion | Glitch | Gateway |  | 3 | aug-31-2015 |  | sep-08-2015 | Repeated with Item66 | Done | sep-08-2015: The actual expectation of this item is same as specified in Item66. Once any module of WAT or SAT completed, It would turn Green and as a result system would recognize its completion
74 | Accessed my Healthy and Safety program - clicked on Module 2 - reviewed module - did not complete the test, went back to my H&S program module missing and removed from data section and points also removed and went down one level | Glitch | Gateway | 1 | 8 | aug-31-2015 |  | oct-18-2015 | Enhancement and Relevant to Item72 | Done | sep-01-2015 [Kartik]: I believe here, tasks is from the Awareness Training(specified module2), I am not getting how it's connected to "My Healthy and Safety program" which is actually My Library | [Sep-02-2015] Kartik, this is because users can see their modules in their My HS Program Training, so once you have done the item 72 above, only make sure here that system show all Workers module as in one tile only if they complete successfully all 4 worker modules, and same for SAT.
75 | Home profile - Message box image error | Glitch | Gateway |  | 1 | aug-31-2015 |  | sep-02-2015 | Glitch | Done |  | Check with new user without message
76 | On Profile Home - Profile Image tile - click image box should allow to insert/edit image | Enhancement | Gateway | 2 | 4 | aug-31-2015 |  | oct-13-2015 | Enhancement | Done
77 | Setting - My professional - Employer drop down should say: -Employed, - Self-Employed, - Unemployed, | Enhancement | HRQ |  |  |  |  | Sep-08-2015 |  | Done |  | HRQ - insert status "Employed"
78 | My Professional - cannot select worker type (JHSC, Sup, Project Manager or language currently there) | Enhancement | S1 | 29 | [7 empty] | S1 will provide text to insert on modal telling designations only from Employer
79 | My Personal - Address needs to be optional | Enhancement | Gateway | 15 | 1 | aug-31-2015 |  | sep-23-2015 | Enhancement | Done
80 | My Personal - Remove Date of Birth and add age box | Enhancement | Obsolete | Obsolete | 1 | aug-31-2015 |  |  | Obsolete |  |  | [Sep-21-2015] It is obsolete, I have checked, we have the Date of Birth on our database and system can easily calculate the age of any S1 users.
81 | My Personal - Password - should say edit password | Enhancement | HRQ | 23 | 30m |  |  | Sep-13-2015 |  | Done
82 | Every profile created, each new user gets 50 credits | Enhancement | Gateway | 41 | 3 | aug-31-2015 |  | oct-03-2015 | Enhancement | Done
83 | Buy Credits - When click on Icon window required to state Once you've selected credit package and click, it should take you to Shopping cart | Enhancement | Gateway | 40 | 1 | aug-31-2015 |  | oct-02-2015 | Enhancement | Done |  | Remove messages notification in the right side and only once bought credit, goes straight to shopping cart.
84 | Profile settings - S1 Rewards image too dark | Enhancement | HRQ |  | 1 |  |  | Sep-19-2015 |  | Done |  | HRQ - replace to logo image from s1 black gray image
85 | DATA - User Tulia Shows 2 inspections data incorrect should show 0 | Review | Gateway |  | 3 | aug-31-2015 |  | sep-03-2015 | Working Fine | Done | sep-03-2015 [Kartik]: I have check that there is not inspection purchased by tulia@surgelearning.ca and also didn't find any library item in the Purchased Tab of H&S program. Please share the exact url where you are getting 2 inspections | Check with a new user, check if in the database the previous user tulia@surgelearning.ca had already any inspections purchased.
86 | DATA - User Tulia shows 3 completed - it should count WAT as one completed | Repeated | Repeated | [6 empty] | Repeated |  | Repeated, item 72 above.
87 | My DATA - main page - Shows Union and flag images - Remove | Enhancement | HRQ | [6 empty] | Done |  | Change it and empty it.
88 | My Data - Points/Credits on lower level incorrect (icon is missing) | Incomplete | HRQ | [6 empty] | Done
89 | My Union - JH&S Rep and Shop Steward cannot select - should auto-populate from profiles | Enhancement | S1 | 25 | [7 empty] | HRQ - modal My Union, should say that designations come from Union/Employer, content will be provided by S1
90 | Select Industrial - All Industrial Sectors need to be available. This also applies to Industrial trades | Enhancement | S1 | [6 empty] | S1 |  | S1 to submit content onto Admin menu
91 | Know Your Rights - Minimum Wage Chart - Add table for Young workers | Enhancement | HRQ | [6 empty] | Done |  | HRQ - take most completed chart from Know your rights and paste into Young Workers.
92 | Skilled Job section - Select one - Viewer window does not enlarge to full screen | Enhancement | HRQ |  |  |  |  | Sep-02-2015 |  | Done |  | Create Modal full screen
93 | S1 Library - Move Ad tiles to bottom of page (horizontal) | Enhancement | On Hold | 21 | 2 | [6 empty] | [Sep-16-2015] Put on Hold as per Tulia request.
94 | Hazard Alerts Tiles - Click on Title - Needs to say "Hazard Alerts" If none - needs to say "No Hazard Alerts" | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done |  | Once there is no Hazard Alerts, switch from "No Alerts Found" to "Hazards Alerts"
95 | Hazard Alerts - If there is no Hazard alerts, do not open modal | Enhancement | Gateway |  | 1 | aug-31-2015 |  | oct-01-2015 | Enhancement | Done |  | Do not open Modal if there is no Hazards Alerts.
96 | Messages - Drop down menu of connections (message needs to say "Can only see message connections). Cannot send message to external email (bottom line messaging does not work) | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done |  | HRQ insert message for connections on modal of compose message, label "You can only messaging connections."
97 | Safety Equipment - Click on button (earned points prior completing questions) - Questions missing | Glitch | Gateway | 1 | 3 | aug-31-2015 |  | sep-16-2015 | In Pipeline | Done | sep-01-2015: Not a Glitch,This task was already in pipeline and put on hold due to priority changes to work on Glitches after post launch | Remaining item from last week.
98 | ON. H&S network - missing MOL Info | Enhancement | HRQ | 10 | 2 |  |  | Sep-19-2015 |  | Done |  | S1 agreed to insert it post launch
99 | About Us - Add formatting - scroll doesn't work on IPad | Glitch | Gateway |  | 2 | aug-31-2015 |  | sep-05-2015 | Working fine | Done | sep-05-2015 [Kartik]: I have check in iPad mini with both portrait and landscape mode, I am able to scroll within the About Us modal | Check with responsiveness team
100 | About Us - Contact Us does not work - Where does it go? Why do we need to input email? | Glitch | HRQ | [6 empty] | Done |  | It is working but not to Info, remove my e-mail and check with Phill.
101 | Login - Landing page - Remove "Get Sign up email" | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done |  | Remove it.
102 | Profile Settings - Fatality breakdown words bigger than box (tablets) | Glitch | HRQ | [6 empty] | Done |  | HRQ - create two line for fatality breakdown
103 | Points on Digital Hazards - Gives points before viewing hazards | Glitch | Gateway | 1 | 3 | aug-31-2015 |  | sep-22-2015 | Improvement before post launch | Done | sep-01-2015: Not a Glitch,This task was already in pipeline and put on hold due to priority changes to work on Glitches after post launch | Remaining item
104 | Digital Hazard - Contact with overhead powerlines - modal does not open correctly (review all digital hazard modal windows) | Review | HRQ |  | 1 |  |  | Sep-19-2015 |  | Done |  | Tulia's computer, Chrome browser, Tulia will send screenshot to find out solution [Sep-10-2015] Need 1h to check all modal in all browsers, if any action is required, more time will be needed. [Sep-10-2015] Checked in chrome, safari, Firefox and I.E., no issues.
105 | Digital Hazard - video "site office" video continues to play after closing | Glitch | Gateway |  | 1 | aug-31-2015 |  | sep-05-2015 | Glitch | Done |  | Do the same applied on Fatality Breakdown
106 | Once reach level 2 - need pop up window to identify achievement | Incomplete | Gateway | 16 | 1 | aug-31-2015 |  | sep-24-2015 | Incomplete | Done |  | Once user reached level 2, a popup window should display it as: You have reached Level [999], [999] points are required to next level.
107 | S1 Library - Training -1 SAT & 1 WAT - XP 100 points each | Incomplete | Gateway | 1 | 6 | aug-31-2015 |  | oct-18-2015 | Enhancement | Done | sep-01-2015 [Kartik]: NOT GETTING sep-03-2015 [Kartik]: Ok got this item now. This is an Enhancement because We come to know in this list itself on the 100 points each for WAT and SAT | India, switch all modules into one item, points will be the total of points 25 x 4. [Sep-02-2015] Kartik, this is related to item 72 above, each piece of Worker Awareness Training gives 25 points, once user completes all 4 items, system should show only one tile and this tile should show 100 points.
108 | Safety Talks - Label requires price & XP. | Incomplete | HRQ | 24 |  |  |  | Aug-27-2015 |  | Done
109 | Shopping cart modal to reflect XP & Credit style applicable to all purchases | Incomplete | HRQ | [6 empty] | Done
110 | Hazards - Drop down - select all does not function | Glitch | Gateway |  | 1 | aug-31-2015 |  | sep-03-2015 | Change Request | Done | sep-01-2015: CHANGE REQUEST | Remove "ALL" from Hazards Filter.
111 | S1 to Review Hazard description for each hazard | Review | S1
112 | S1 Library hazard remove word construction from titles | Enhancement | HRQ | [6 empty] | Done |  | HRQ, priority 1, apply it to Digital Hazards
113 | Procedures - Procedures inactive, prices incorrect, missing descriptions | Incomplete | HRQ | [6 empty] | Done
114 | Inspections - Drag and drop not functioning 100% | Glitch | Gateway | 1 | 4 | aug-31-2015 |  | sep-11-2015 | Glitch | Done | sep-01-2015 [Kartik]: Need to check the existing functionality sep-11-2015: This has been done and so customized inspections going to drag&drop section. | Inspections -Ladder group - system does not allow to add this to drag and drop box, Customized Inspections not going to drag and drop section.
115 | S1 Inspections - Modal of purchase confirmation is going under tiles, rezone it. | Glitch | HRQ | [6 empty] | Done
116 | S1 Inspections - buying by drag and drop does not appear in my h&s program my inspections | Glitch | Gateway |  | 4 | aug-31-2015 |  | sep-07-2015 | Glitch | Done | sep-01-2015 [Kartik]: Need to check the existing functionality sep-07-2015: This has been done
117 | S1 Inspections - Change label to "Drag and Drop" | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done
118 | S1 create explanation of inspections (how to create customized inspections) | Enhancement | S1 | [8 empty] | S1 will provide content
119 | Investigations - Price review(done) - Info button update | Incomplete | S1 | [8 empty] | HRQ Ricardo has right prices to change Sep-10-2015 - Prices updated, description will be provided by S1
120 | Worker Profile - DROT - add message that can only view DROT once assigned by your employer. Connect to your employer | Enhancement | Gateway | 17 | 1 | aug-31-2015 |  | oct-01-2015 | Enhancement | Done |  | If there is no BADGES assigned (workers), page should show :"NO DROTs have been assigned by your employer"
121 | Assign DROT for WAT/SAT completion, once user complete WAT or SAT, system should assign a D.R.O.T to him | Enhancement | Gateway | 1 | 8 | aug-31-2015 |  | oct-13-2015 | Enhancement | Done | sep-01-2015 [Kartik] - If user finish WAT or SAT from the Awareness Training module, then which D.R.O.T need to assign to user. Not getting this point exactly | Create relationship among WAT, SAT and DROT, pre-populated with: Provider type: S1 Provider name: s1 Location: online Instructor Name: s1 [Sep-02-2015] For WAT, badge id=33. For SAT, badge id=32. User will get these badges, and they should appear in their Id Card and my DROT page, with content above.
122 | Connection to local 183 - did not request member status windows | Working | OBSOLETE | [6 empty] | Done |  | Tested today Sep-01-2015 at 2:40am, it is working.
123 | MOL enforcement stats - Info button descriptions missing for remaining pages | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done |  | HRQ - it will be only one description. Priority 1
124 | Languages for Digital Hazards | Enhancement | Gateway | 11 | 5 | aug-31-2015 |  | sep-29-2015 | Enhancement | Done
125 | LIUNA 183 Participant portal - 1 click access | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done |  | HRQ - hit Participant Portal MENU and goes straight to Participant portal page, remove slider and button.
126 | MY DATA - Profile image duplicated, remove the second. - added Sep-02 | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done
127 | GET STARTED - TRAINING - SKIP - change image | Glitch | HRQ |  |  |  |  | Sep-03-2015 |  | Done
128 | ASSIGN LIBRARY - if user select more than one library to assign, the warning popup comes with the message "Successfully Assigned" repeatedly. | Glitch | GATEWAY |  | 1 | sep-03-2015 |  | sep-03-2015 | Glitch | Done
129 | SHOPPING CART - KEEP SHOPPING - target to S1 Library | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done
130 | SAT - Remove words "do not" under image description for WHMIS | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done
131 | SAT - MODULE 2 - update wage table | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done
132 | SAT - MODULE 4 - remove image | Glitch | HRQ |  |  |  |  | sep-02-2015 |  | Done
133 | WAT - MODULE 1 - update wage table | Enhancement | HRQ |  |  |  |  | sep-02-2015 |  | Done
134 | WAT - INSPECTION - Remove relationship from s1 libraries in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
135 | WAT - INSPECTION - Insert static content provided by S1 Team in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
136 | WAT - DUE DILIGENCE - Remove relationship from s1 libraries in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
137 | WAT - DUE DILIGENCE - Insert static content provided by S1 Team in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
138 | WAT - PROCEDURES - Remove relationship from s1 libraries in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
139 | WAT - PROCEDURES - Insert static content provided by S1 Team in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
140 | WAT - INJURIES - Remove relationship from s1 libraries in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
141 | WAT - INJURIES - Insert static content provided by S1 Team in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
142 | SAT - INSPECTION - Remove relationship from s1 libraries in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
143 | SAT - INSPECTION - Insert static content provided by S1 Team in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
144 | SAT - DUE DILIGENCE - Remove relationship from s1 libraries in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
145 | SAT - DUE DILIGENCE - Insert static content provided by S1 Team in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
146 | SAT - PROCEDURES - Remove relationship from s1 libraries in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
147 | SAT - PROCEDURES - Insert static content provided by S1 Team in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
148 | SAT - INJURIES - Remove relationship from s1 libraries in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
149 | SAT - INJURIES - Insert static content provided by S1 Team in all 4 Modules | Enhancement | HRQ |  |  | Sep-04-2015 |  | Sep-08-2015 |  | Done
150 | PROFILE CREATION - My data page (MY SETTINGS), switch label to USER PROFILE SETTINGS | Enhancement | HRQ | 1 | 15m | Sep-09-2015 |  | Sep-13-2015 |  | Done
151 | PROFILE CREATION - For EMPLOYER, my data page form should be different than others, with following fields: Company Name, Company Full Address, E-mail, Confirm e-mail, password, confirm password. | Enhancement | Gateway | 2 | 3 | Sep-09-2015 |  | sep-30-2015 | Enhancement | Done
152 | PROFILE SETTINGS - FOR EMPLOYER - Insert WSIB Rate Group, list already provided by Phill, on Professional Settings as not required field. | Enhancement | Gateway | 3 | 5 | Sep-09-2015 |  | sep-23-2015 | Enhancement | Done | sep-21-2015: Please send the WSIB Rate Group list, I saw pdf file about the same, however let me know which data would be required | [Sep-21-2015] Kartik, see tab below named "WSIB-RateGroup" to be implemented as per this request, please create maintenance abilities on S1 Admin/menu.
153 | WAT/SAT - Implement translation tools on Inspections, Due Diligence, Procedures, Injuries MODALS Note: Translation will not be applied on GLOSSARY modal. | Enhancement | Gateway | 4 | 10 | Sep-09-2015 |  | oct-03-2015 | Enhancement | Done | sep-11-2015: I had started to work on this as per the Priority set as "High" and now changed it to 4, so I had put on hold.
154 | S1 LIBRARY VIEW - Procedures bottom modal - fix standard tile view in the related list | Glitch | HRQ | 6 | 0 | Sep-10-2015 |  | Sep-10-2015 |  | Done
155 | S1 LIBRARY VIEW - Procedures bottom modal - Insert image and description same applied to WAT above tiles | Enhancement | HRQ | 7 | 30 | Sep-10-2015 |  | Sep-10-2015 |  | Done
156 | S1 LIBRARY VIEW - Inspections bottom modal - check standard tile view in the related list | Glitch | HRQ | 8 | 0 | Sep-10-2015 |  | Sep-10-2015 |  | Done
157 | S1 LIBRARY VIEW - Inspections bottom modal - Insert image and description same applied to WAT above tiles | Enhancement | HRQ | 9 | 30 | Sep-10-2015 |  | Sep-10-2015 |  | Done
158 | WAT/SAT - PROCEDURES TILE - Remove "or by a Ministry of Labour Inspector" from the text | Enhancement | HRQ | 1 | 10 | Sep-10-2015 |  | Sep-10-2015 |  | Done
159 | MY H&S PROGRAM - Inspections bottom modal- Remove link to actual content, remove function to buy from modal, display only a maximum of 4 items | Enhancement | HRQ | 1 | 60 | Sep-10-2015 |  | Sep-10-2015 |  | Done
160 | MY H&S PROGRAM - Procedures bottom modal - Remove link to actual content, remove function to buy from modal, display only a maximum of 4 items | Enhancement | HRQ | 1 | 40 | Sep-10-2015 |  | Sep-10-2015 |  | Done
161 | MESSAGE COMPONENT - For any message send by S1 as connection request, accept, remove, badges, inspection, investigation, etc. System should keep the message within message module, and send same e-mail to user's e-mail account. | Enhancement | Gateway | 1 | 6 | Sep-17-2015 |  | oct-12-2015 | Enhancement | Done |  | Please estimate time to deliver it
162 | EMAIL - Design standard e-mail to match item 161 | Enhancement | HRQ |  | 2 | Sep-17-2015 |  | Sep-28-2015 |  | Done
163 | PROCEDURES - Upload Photos & Videos - allow Admin and users to upload photos and videos on procedures (procedures section), same criteria applied on Union Hazard alerts. | Enhancement | Gateway | 2 | 6 | Sep-17-2015 |  | oct-17-2015 | Enhancement | Done |  | Please estimate time to deliver it
164 | BUY PLATINUM CREDITS - if user has requested special package, while he does not pay, he is not able to request other package. System should allow him to sent requests for more packages, admin will find out the number of requests. | Glitch | Gateway |  | 2 | Sep-17-2015 |  | oct-02-2015 | Change Request | Done | sep-21-2015 [Kartik]: This is not a glitch, as per the previous request only, we had implement this restriction. We would change now as per the current request. | Please estimate time to deliver it
165 | BUY PLATINUM CREDITS - Admin should get e-mail and s1 message in his inbox notificating the request. | Enhancement | Gateway | 1 | 3 | Sep-17-2015 |  | oct-09-2015 | Enhancement | Done |  | Please estimate time to deliver it
166 | BUY PLATINUM CREDITS - S1employer requested, admin set price as $5000, s1employer has not paid, S1 changed the price to $3500 but it didn't changed s1employer shopping cart amount. | Glitch | Gateway | 1 | 4 | Sep-17-2015 |  | oct-30-2015 | Enhancement | Done | oct-27-2015 [Kartik]: This is not a Glitch, as Now Platinum credits could be purchasable for more than 1 time by any user, So I have provided credits listing with status of credits request, So if admin update the price of specific credit entry then it would update in the credits listing of Platinum Model. | Please estimate time to deliver it
167 | ASSIGN CREDITS - Admin should be able to give/assign credits to one or more users. | Enhancement | Gateway | 2 | 9 | Sep-17-2015 |  | oct-29-2015 | Enhancement | Done |  | Please estimate time to deliver it
168 | REWARDS SYSTEM - Create new user, test the reward: 1. Receive Points XP 2. Unlock Reward Code | Enhancement | HRQ |  | 3 | Sep-19-2015 |  | Sep-21-2015 | Enhancement | Done
169 | REWARDS SYSTEM - Popup for Level Design Modal for becoming Level up, if 2 "You Rewards Have Unlocked" | Enhancement | HRQ |  | 2 | Sep-19-2015 |  | Sep-25-2015 |  | Done
170 | REWARDS SYSTEM - Insert message into Profile Id-Card "Your Rewards have been unlocked.", once he reaches level 2. | Enhancement | HRQ | k | 2 | Sep-19-2015 |  | Sep-21-2015 |  | Done
171 | DROT - WAT/SAT - Design modal to display when user finish training | Enhancement | HRQ | k | 2 | Sep-19-2015 |  | Sep-25-2015 |  | Done
172 | CONSULTANT PAGE - test functions as per the request | Enhancement | HRQ/Phill | 1 | 3 | Sep-19-2015 | Nov-11-2015
249 | DIGITAL HAZARDS FOR OFFICE - Translation component is not changing language once select combo box is clicked, only if you close and open the modal. *** This is a remaining subtask from item 243 above, to be completed by Gateway | Enhancement | Gateway | 1 | 3 | Nov-23-2015 |  | Nov-23-2015 | Enhancement | Done
174 | REVIEW SYSTEM - Testing every function and review Gateway testing | ON HOLD | ON HOLD | ON HOLD | 80 | Sep-19-2015 |  |  |  | ON HOLD
175 | EMPLOYER SIGN UP - Change form requested for Employers signing up, add fields below: . Company name; . Company full address | Enhancement | Gateway |  | 4 | Sep-19-2015 |  | oct-02-2015 | Enhancement | Done
176 | ADMIN DATA COLLECTION - analyse scripts | Enhancement | HRQ |  | 5 | Sep-19-2015 |  | Sep-24-2015 |  | Done |  | [Sep-24-2015] After analysis, perhaps it requires further clarification prior to send it to development.
34 | INVESTIGATION - First Aid - Add N/A to all sections in investigations | Enhancement | Gateway | 3 | 16 | aug-31-2015 |  |  | Enhancement |  |  | For all sections add N/A with checkbox, when it is checked, this will not be open or printed. Some sections are not required for real world investigation.
178 | UNION DATA COLLECTION - analyse scripts | Enhancement | HRQ | k | 5 | Sep-19-2015 |  | Sep-24-2015 |  | Done
49 | My HS Program, once finished testing nothing happens. After completed, system should send user to initial page for this specific content, with a Modal telling “You have completed the [title] ”. | Gap | Gateway | 3 | 7 | aug-31-2015 |  |  | Gap |  | sep-01-2015: Timelines shared if it's required to implement modal for all library types
180 | “Set of Rules” document that we use to ensure content is submitted and uploaded within the programming parameters of the system. This includes sections on: a. Content Formatting (size, amount of characters per page, bullets, roman numerals etc.) b. Content Uploading (including best way for us to do this, direct, use notepad first etc.) c. Media Rules (what sizes, images etc.) | Gap | HRQ | 3 | 12 | Oct-05-2015
181 | LIBRARY UPDATE/INSERTION - Update Admin portal view to create a “preview” window to allow the content uploader to see the content from an “active” view prior to activating the content for use. | Enhancement | HRQ | 1 | 4 | Oct-05-2015 |  | Oct-24-2015 |  | Done
182 | LIBRARY ICONS - Ensure all the Icons throughout the system are correct | Gap | HRQ | 1 | 4 | Oct-05-2015 |  | Oct-27-2015 |  | Done
183 | Organize all administrators and provide them with separate user names and passwords | Enhancement | ON HOLD | 3 | 2 | Oct-05-2015 | [5 empty] | [Nov-18-2015] Item on hold as per our talking in the meeting today.
184 | Construction Hazard - Inspections button i. Need to move the inspection paragraph to the top of the page, then insert the image, then enter the related inspections. iii. Ensure Names are removed from the content boxes – leave blank or enter John Doe. v. Under Hazard Related title remove “S1 Message” | Enhancement | HRQ | 1 | 2 | Oct-05-2015 |  | Oct-26-2015 |  | Done
185 | Construction Hazard - Inspections button ii. Relevant screen shots of inspection piece to be inserted (Vanessa to provide). | Enhancement | HRQ | 1 | see comments | Oct-05-2015 |  | Nov-09-2015 |  | Done |  | [Oct-05-2015] Can't estimate time while I don't have the images, but it could be from 2 to 4 hours
186 | Construction Hazard - Inspections button iv. Develop translation button | Enhancement | Gateway | 1 | 2 | Oct-05-2015 |  | oct-07-2015 | Enhancement | Done
187 | Construction Hazard - Due Diligence button i. Remove Due Diligence title and hard coded title (the title in the red bar as part of the pop up screen will be the only title used) ii. Remove OHSA 213/91 from title, they are individual regulations not one. iv. Rename Reg. 213/91 to say O. Reg 213/91 Construction Projects | Enhancement | HRQ | 1 | 2 | Oct-05-2015 |  | Oct-28-2015 |  | Done
188 | Construction Hazard - Due Diligence button iii. Make sure all sections link to the right regulation section and that all links work. | Testing | HRQ | 1 | 4 | Oct-05-2015 |  | Oct-28-2015 |  | Done
189 | Construction Hazard - Due Diligence button v. Only enter the section and sub section for the regulation being sited and ensure the pop up screen identifies all sub sections within it: Due Diligence Button: Hazard Content sent by S1: O. Reg 213/91 Construction Projects Traffic Control: section 67(6)(a)(b)(c) How it should look in the system: O. Reg 213/91 Construction Projects Traffic Control: Section 67(6) **Reader clicks on this and can now read section 67(6)(a)(b)(c) within the pop up screen. | Enhancement | Gateway | 1 | 6 | Oct-05-2015 |  | oct-12-2015 | Enhancement | Done
190 | Construction Hazard - Glossary button i. Remove the two Glossary titles (blue with line copied and pasted from content, and hard coded grey title hardcoded from the content upload template). ii. Ensure only one title remains – the “button” title with red border. | Enhancement | HRQ | 1 | 1 | Oct-05-2015 |  | Oct-26-2015 |  | Done
191 | Construction Hazard - Procedure button i. Place procedure paragraph at the top of the page, followed by procedure image, then hazard related procedure section. ii. Fix typo from Hazards Related Procedure to Hazard Related Procedure (remove the s from hazards) iv. Remove Procedures inserted title (Blue with line) Keep only the “button” title with red border. vi. Change the paragraph under Hazard Specific Procedure to say Some hazard related procedures are listed here, you can find more procedures in the S1 Library. | Enhancement | HRQ | 1 | 2 | Oct-05-2015 |  | Oct-26-2015 |  | Done
192 | Construction Hazard - Procedure button iii. Create translation button | Enhancement | Gateway | 1 | 3 | Oct-05-2015 |  | oct-07-2015 | Enhancement | Done
193 | Construction Hazard - Procedure button v. Insert new procedure specific screen shots (provided to you by Vanessa). | Enhancement | HRQ | 1 | see comments | Oct-05-2015 |  | Nov-10-2015 |  | Done |  | [Oct-05-2015] Can't estimate time while I don't have the images, but it could be from 2 to 4 hours [Nov-09-2015] Some pictures still outstanding to upload.
194 | Construction Hazard - Injuries button: i. Enter title: Hazard Specific Injuries (use same formatting as Hazard Specific Procedures). iv. Re-size boxes so that titles are clearly visible. | Enhancement | HRQ | 1 | 2 | Oct-05-2015 |  | Oct-26-2015 |  | Done
195 | Construction Hazard - Injuries button: iii. Create translation button | Enhancement | Gateway | 1 | 8 | Oct-05-2015 |  | oct-07-2015 | Enhancement | Done
196 | Construction Hazard - Injuries button: ii. Insert Paragraph: Listed here are injuries that are commonly associated with this hazard. Click on one of the injuries below to get a full description. | Enhancement | HRQ | 1 | 4 | Oct-05-2015 |  | Oct-27-2015 |  | Done
197 | Construction Hazard - Media Button: i. Insert all images located in the pages of this hazard into the media section. | Enhancement | Gateway | 1 | 8 | Oct-05-2015 |  | oct-09-2015 | Enhancement | Done
198 | Construction Hazard - Icons: Ensure all icons are correct. | Enhancement | HRQ | 1 | 2 | Oct-05-2015 |  | Oct-27-2015 |  | Done
199 | Construction Hazard - Main Hazard View: i. Remove the titles from all main pages, and ensure the first line/title is Definition (in blue and underlined) - done ii. Remove all “*” and replace with bullets iii. Ensure each Large Blue Title as a 2inch thick blue line under it. iv. Ensure font size 12px in all pages | Enhancement | HRQ | 1 | 16 | Oct-05-2015 |  |  |  | Done |  | [Oct-29-2015] Done for Hazards: 372, 182, 305, 306, 307, 308, 309. Still outstanding Hazards: 362, 135, 311, 138, 312, 315, and others still inactive under finalization. [Oct-30-2015] Item 199, done for all active Hazards: 262, 135, 311, 138, 312, 315
200 | YOUNG WORKERS - Insert images for data and ensure titles match | Enhancement | HRQ |  | 1 | Oct-22-2015 |  | Nov-10-2015 |  | Done
201 | MOL - Insert Enforcement buttons at the end of the tiles for Ontario Fatalities and Injuries Stats | Enhancement | HRQ |  | 1 | Oct-22-2015 |  | Nov-03-2015 |  | Done
202 | DIGITAL HAZARD - make stats wider | Enhancement | HRQ |  | 1 | Oct-22-2015 |  | Nov-03-2015 |  | Done
203 | WAT/SAT - Review DROT ASSIGNED. | Testing | HRQ/Phill |  | 2 | Oct-22-2015 | Nov-11-2015 |  |  | In progress 95% |  | [Nov-09-2015] Purchased, assigned, worker received msg in the message module, notification working, employer inventory worked. Checked database integrity. Needed to check if external e-mail is required for this function, haven't tested it.
204 | HAZARDS - INJURIES MODAL - If Injury has more than one image in its slider, tabs don't work | Glitch | Gateway | 1 | 3 | Oct-22-2015 |  | oct-27-2015 | Glitch | Done | oct-27-2015 [Kartik]: This has been done and uploaded on the live site, Data of "Spinal Cord Injury" tab was making issue while Google translation, which has been implemented with other way. | See this issue loading hazard id 308 (Fall From Heights Hazard) as s1employer and open the Injury "Spinal Cord Injury". [Oct-23-2015] In the same cases where we have more than one image, if you click over the tabs, the content has been repeated, it seems like it is loading all pages in one tab...
205 | HAZARDS - INJURIES MODAL - verify responsiveness of images slider | Testing | HRQ |  | 1 | Oct-22-2015 |  | Nov-03-2015 |  | Done
206 | SIGNUP Warning - first warning is not displaying well | Glitch | HRQ |  |  | Oct-27-2015 |  | Oct-28-2015 |  | Done
207 | SIGNUP Password - display msg for required characters on password field | Enhancement | HRQ |  |  | Oct-27-2015 |  | Oct-28-2015 |  | Done
13.1 | Due Diligence section of new procedure - Once select section should have ability to type. When typed 22 takes you to 20 in the drop down list Ability to see wording for selected regs. | Enhancement | Gateway | 2 | 4 | aug-31-2015 |  | nov-30-2015 | Enhancement | Done | aug-31-2015 [Kartik]: This is the generic behaviour of the any box when you type and searching as per the number typed. Though we will check and try to do as per the expectations | For items under regulation, we need to implement a script or element to allow users to select by the standard way, and type and search for specific item...
19 | PROCEDURES - DUE DILIGENCE - Additional Regs - Show sections & wording | Enhancement | Gateway | 3 | 6 | aug-31-2015 |  |  | Enhancement | Partially Done | aug-31-2015 [Kartik]: Not getting sep-01-2015: Sorry but for which module are you talking about. dec-22-2015 [Kartik]: I had started this task because it was linked up with other higher priority items, then this was put on hold due to other higher priority tasks | Once user select one regulation, system should show the content for each item, but not the full regulation, only the item selected. [Sep-02-2015]Kartik, this is related to PROCEDURES/ DUE DILIGENCE SECTION, I have inserted it into the title right now.
208 | HAZARD - DUE DILIGENCE - Bring and display Part and Subpart in each regulation related | Enhancement | Gateway |  | 4 | Oct-28-2015 |  | nov-02-2015 | Enhancement | Done | nov-02-2015 [Kartik]: Actually Regulation Content Id is superior than regulation number, section, subsection, item, subitem and while making the library regulation relation, we are not asking the Regulation Content relevant data such as part and subpart, that's why I did not add Title, Part and Subpart in the "tbl_library_regulation" table. Now as per this Item I had stored, i) in_parent_regulation_id in tbl_regulation_sections table. ii) in_parent_regulation_id, in_regulation_content_id in tbl_library_regulation table. | [Oct-28-2015] After enhanced script and view for Due Diligence Modal on Hazards, I have seen that the sql scripts bring regulation from table tbl_library_regulation, but this table does not have title, part and subpart for each regulation, only library_id, reg number, section, subsection, item and subitem. We need to do either insert Regulation Id in this table, or add title, part and subpart, in order to bring from table tbl_regulaton_contents and display into the main modal and sub-modal reg number, title, part and subpart to make the view easier for any user.
209 | MY HAZARDS - PURCHASED - XP = 0 - My Library/Hazards bringing points "xp = 0 ", please check it in all libraries into my library table on database. See my comments in the last column of this sheet. | Glitch | Gateway |  | 2 | Nov-03-2015 |  | nov-04-2015 | Glitch | Done | nov-04-2015 [Kartik] - Credits are going in correct manner while purchasing the library item now. I found some of the old data with 0 credits(points) in the tbl_my_library table, so I have updated the same on live database too. | [Nov-03-2015] For Hazards purchased by credits, the field "credits"(points) on table tbl_my_library is coming with value = 0, making the system display "0" after the icon xp, "xp 0" within the tiles. Please it should come with their right points. Please check the sql scripts below and compare the results. SELECT * FROM `tbl_my_library` WHERE `credits` = 0 ORDER BY `user_id` ASC SELECT * FROM `tbl_my_library` WHERE `credits` != 0 ORDER BY `user_id` ASC
210 | GET STARTED - DASHBOARD - Completion of Get Started does not avoid "Welcome" image being displayed on Dashboard - see further comments in proper column | Glitch | Gateway |  | 2 | Nov-04-2015 |  | nov-052015 | Glitch | Done |  | [Nov-04-2015] Tested today as s1employer, all sections on Get Started page were checked with green border, however the splash image for Welcome on Dashboard keep being displayed.
213 | QUIZ MODULE - change bullet to letter a, b, c, d....on quiz module. | Enhancement | HRQ |  | 1 | Nov-10-2015 | Nov-10-2015 | Nov-10-2015 |  | Done
214 | H&S PROGRAM - Review and fix tiles on H&S Program | Glitch | HRQ |  | 4 | Nov-10-2015 |  | Dec-16-2015 |  | Done |  | [Dec-15-2015] Remaining: Procedures(partially done), Inspections and Investigations.
215 | H&S PROGRAM - Review and fix hover message description on H&S Program | Glitch | HRQ |  | 4 | Nov-10-2015 |  | Dec-16-2015 |  | Done |  | [Dec-15-2015] Remaining: Procedures(partially done), Inspections and Investigations.
211 | MY PROCEDURES - Pagination - once user has one piece of one procedure, and he assigns it, this procedure rightly disappears of his My Procedures page, however the page counter still counts it, making the page show less items than the total possible, breaking the pagination style. See further comments in proper column. | Glitch | Gateway |  | 1 | Nov-04-2015 |  | nov-052015 | Glitch | Done |  | [Nov-04-2015] I have seen it once I bought the procedure id=129 and assign it to other user, logged as s1employer. The controller still brings the library assigned within array $documents_purchased, does not showing it as tile, but breaks the pagination counter. See scripts below to easier your research and analysis: SELECT * FROM `tbl_assignments` WHERE `library_id` = 129 SELECT * FROM `tbl_my_library` WHERE `user_id` = 20 AND `lib_id` = 129 ORDER BY `date_bought` DESC
216 | INSPECTIONS - completed inspection id 26 on s1 employer, could be able to edit inspection after saved it. | Glitch | Gateway |  | 2 | Nov-10-2015 |  | nov-18-2015 | Glitch | Done
218 | HAZARDS/INJURIES - Mobile - FIREFOX on mobile is not loading images coming from hazards/injuries | Glitch | Gateway |  | 1 | Nov-10-2015 |  | nov-24-2015 | Review | Working fine | nov-24-2015 [Kartik] - Injury modal images showing, as I have check on firefox mobile mode, iPhone6+ and iPad-mini screens. Kindly share in which screens you are facing an issue.
217 | INSPECTIONS - Inspection review fields and sizes for typing as done for investigations | Enhancement | Gateway |  | 1 | Nov-10-2015 |  | nov-18-2015 | Enhancement | Done
220 | HAZARDS/INJURIES/Injury - FIREFOX on Mobile - "x" to close modal quicks user out on mobile. | Glitch | Gateway |  | 1 | Nov-10-2015 |  | nov-24-2015 | Review | Working fine | nov-24-2015 [Kartik] - Injury modal images showing, as I have check on firefox mobile mode, iPhone6+ and iPad-mini screens. Kindly share in which screens you are facing an issue.
221 | RESPONSIVE - Zooming - Allow user to zoom in mobile modal, images, pages, charts | Enhancement | HRQ |  | 3 | Nov-10-2015 | Nov-13-2015 | Nov-13-2015 |  | Done
222 | S1 VIDEOS - review video titles on YouTube store making them match with their purpose. | Enhancement | S1 |  | 4 | Nov-10-2015
223 | S1 LIBRARY - MEDIA BUTTON - do not show title within the video. | Enhancement | HRQ |  | 2 | Nov-10-2015 | Nov-12-2015 | Nov-12-2015 |  | Done
224 | S1 LIBRARY - Implement same notice for Quiz in the last page of Hazards and Trainings | Enhancement | HRQ |  | 2 | Nov-10-2015 | Nov-12-2015 | Nov-12-2015 |  | Done
225 | QUIZ MODULE - Review where S1 have it beyond S1 Library Hazard/Training and implement notice for users to perform it. | Enhancement | HRQ |  | 2 | Nov-10-2015
226 | PROCEDURE - Glossary - Remove section Glossary in every procedure within the system | Enhancement | HRQ |  | 2 | Nov-10-2015 | Nov-13-2015 | Nov-13-2015 |  | Done
227 | HAZARD VIEW - Change the font color to Gray/Black in any header with Yellow background. | Enhancement | HRQ |  | 2 | Nov-10-2015 | Nov-13-2015 | Nov-13-2015 |  | Done
228 | S1 Logo - Responsive - Reduce logo up to 70% in different screen sizes and media queries in order to make the header smaller in mobiles | Enhancement | HRQ |  | 2 | Nov-10-2015 | Nov-13-2015 | Nov-17-2015 |  | Done
229 | OFFICE HAZARD - Review and fix remaining styles glitches from Vanessa's doc "Office Hazard Glitches - October 26, 2015.docx" | Glitch | HRQ |  | 4 | Oct-26-2015 | Nov-23-2015 | Nov-30-2015 |  | Done
230 | PROCEDURES - Review and fix remaining styles glitches from Vanessa's doc "Procedure Issues - October 27, 2015.docx" | Glitch | HRQ |  | 4 | Oct-2-2015 | Nov-19-2015 | Nov-18-2015 |  | Done |  | [Nov-18-2015] Remaining issues related to programming have been already addressed to Gateway as per the items 247 and 248 below.
231 | DUE DILIGENCE - Display Regulations as per Vanessa's request: v. Only enter the section and sub section for the regulation being sited and ensure the pop up screen identifies all sub sections within it: Due Diligence Button: Hazard Content sent by S1: O. Reg 213/91 Construction Projects Traffic Control: section 67(6)(a)(b)(c) How it should look in the system: O. Reg 213/91 Construction Projects Traffic Control: Section 67(6) **Reader clicks on this and can now read section 67(6)(a)(b)(c) within the pop up screen. | Enhancement | HRQ |  | 3 | Nov-02-2015 Dependant of item 208 above | Nov-12-2015 | Nov-30-2015 |  | Done |  | [Nov-19-2015] It is done for Regulation view, however the Due Diligence page should be hidden in Due Diligence Modal, as per meeting with Phill today.
219 | HAZARDS/INJURIES/Injury - "x" to close modal is reloading page and closing main injuries modal, behind the specific injury. This behaviour is not user friendly. | Enhancement | Gateway |  | 1 | Nov-10-2015 |  | nov-18-2015 | Enhancement | Done
233 | INFORMATION FOR CREATING PASSWORD - not well implemented on recovery page as done for signup page. | Glitch | HRQ |  | 1 |  | Nov-20-2015 | Nov-18-2015 |  | Done
234 | DASHBOARD - slider does not fit well on Iphone4S, however it is working well on Profile Home | Glitch | HRQ |  | 2 |  | Nov-27-2015 | Nov-18-2015 |  | Done
235 | (item 1 as per Phill's email - Nov-16) Construction/office Hazard (Injury button) Injury Stats not uploaded - about 30 images | Enhancement | HRQ |  | 2 |  | Nov-20-2015 |  |  | Done
236 | (item 2 as per Phill's email - Nov-16) office Hazards (procedure button) Images not inserted - about 20 procedures | Enhancement | HRQ | 1 | 4 |  | Nov-20-2015 | Nov-20-2015 |  | Done
237 | (item 3 as per Phill's email - Nov-16) office Hazards (inspection) images not inserted - about 20 inspections | Enhancement | HRQ | 1 | 5 |  | Nov-20-2015 | Nov-20-2015 |  | Done
238 | (item 4 as per Phill's email - Nov-16) Construction Digital Hazard stats not updated - about 16 images | Enhancement | HRQ |  | 1 |  | Nov-20-2015 | Nov-18-2015 |  | Done
239 | (item 5 as per Phill's email - Nov-16) Office digital Hazard stats not sure if these have been submitted for review/approval to S1 - about 12 images | Enhancement | HRQ | 1 | 1 |  | Nov-20-2015 | Nov-19-2015 |  | Done
240 | (item 6 as per Phill's email - Nov-16) office digital Hazard upload images - about 50 images | Enhancement | HRQ | 1 | 4 |  | Nov-20-2015 | Nov-19-2015 |  | Done
241 | (item 6 as per Phill's email - Nov-16) office digital Hazard (content previously submitted by Vanessa ) - about 40 sections | Enhancement | HRQ | 1 | 3 |  | Nov-20-2015 | Nov-23-2015 |  | Done
242 | (item 7 as per Phill's email - Nov-16) programming for office Digital Hazards (additional buttons) - Web Design from HRQ | Enhancement | HRQ | 1 | 4 |  | Nov-20-2015 | Nov-22-2015 |  | Done
243 | (item 7 as per Phill's email - Nov-16) programming for office Digital Hazards (additional buttons) - Translating components by Gateway | Enhancement | HRQ | 1 | 2 |  |  | Nov-23-2015 |  | Done |  | [Nov-23-2015] It was done from HRQ, however there is a final element should be implemented enhanced by Gateway, new item 249 has been added in this sheet.
244 | (Item 8 as per Phill's email - Nov-16)- all tests components in the system including Fat Breakdown and PPE (anywhere we have questions) to remove bullets and add A, B, C, D for multiple choice questions (programming) | Glitch | HRQ |  |  |  |  | Nov-18-2015 |  | Done
245 | (Item 9 as per Phill's email - Nov-16) office Dig Hazard Overview scene (completed by S1 and ready for submission) | Enhancement | HRQ |  | 2 |  | Nov-20-2015 | Nov-18-2015 |  | Done
232 | FORGOT PASSWORD FOR INACTIVE USER - coming message for get signup e-mail to get new confirmation, and e-mail not coming. Please implement trigger to get nofification e-mail on signup. | Issue | Gateway |  | 2 |  |  | nov-27-2015 | Change Request | Done | nov-25-2015 [Kartik] - Not an issue. As per the earlier request, "get signup email" link has been removed from the Login page. Now in this schenario, We could enable "get signup email" only if user is inactive and click on "forget password". Let me know if it's perfect for you. nov-27-2015 [Kartik] - Yes right, I would just put 1 static indication message for user, once "inactive" user click on forgot password. | nov-26-2015 [Marcio] - Yes, I agree with your thoughts in the sheet. Just for double check, if user is "inactive" and click "forget password", system will trigger the signup email straight to user e-mail registered, without asking any other action into this page, only reading his e-mail with the link and password for activation right?
246 | (Item 10 as per Phill's email - Nov-16) PPE questions outstanding that require to be inserted (Nurse, Fire fighter, hockey player) | Enhancement | Gateway |  | 5 |  |  | nov-28-2015 | Enhancement | Done | nov-25-2015 [Kartik] - I have only questions of Nurse, however please share the questions of Fire fighter and Hocky, Though I have mention timeline. | nov-26-2015[Marcio] - It is attached into this reply+
247 | PROCEDURES - Section Procedures/itens, admin is not able to insert single or double quote, it brings sql sintax error. See further comments in proper column. | Issue | Gateway |  | 1 | Nov-18-2015 |  | Nov-19-2015 | Issue | Done |  | [Nov-18-2015] these items have been recorded at tbl_proc_procedures, column st_procedures_items as type text in a group between double quotes. My suggestion would be change the way to save these items in the database, doing it in other table and change the data type to accept these symbols. I have tried with html code &#39; but it does not work for preview, however admin is not willing to insert this code. Check procedures id: 240, 253, 250, 249 and 246. All of them have one or more items with single quote and system is breaking.
248 | PROCEDURES - SECTION MACHINERY - items added on Machinery Modal are not being displayed on Preview. See procedure id: 245 | Issue | Gateway |  | 1 | Nov-18-2015 |  | Nov-19-2015 | Issue | Done
250 | MOL PAGE - Change menu labels as per Phill request on Nov-20-2015: 2- left Navigation Bar : "Fatality " button should say "Total Ontario Fatalities " 3- "Injury" button should say " Total Ontario Injuries" | Enhancement | HRQ |  | 0.25 | Nov-23-2015 |  | Nov-30-2015 |  | Done
251 | HAZARD TESTING LAST PAGE - once user add more pages, script for test/quiz does not recognize the new last page, and become enabled in the wrong page, please find further comments in the proper column. | Issue | Gateway |  | 3 | Nov-23-2015 |  | nov-27-2015 | Change Request | Done | nov-24-2015 [Kartik] - Not an Issue. Access of quiz section and "test/summary" images has been implmented dynamically in such as way that if specific page has quiz entered in the database then only quiz section would be activated, irrespective of any page you are viewing. I remember it was decided that quiz would be entered on the last page of the library. nov-27-2015 [Kartik] - Ok. I would do the same as per this change request | [Nov-23-2015] Kartik, see below e-mail from admin user explaining further more the issue: As per our discussion this morning please find below the ID of one of the office hazards with regard to the test static image on page 6 where the questions were inputted instead of at the end of the document. Also the test is only activated on page 6, when you go to page 7-9 (which were added just recently) the test button is not active and cannot be selected. Electrical Hazard ID: 332 (but I believe all of them have the same issue) nov-26-2015 [Marcio] - You are right, we decide to control it by the manual process, however a necessity came up later on, so could you please make the quiz appears only in last page, no matter if it was inserted in any other page?
252 | Update Library - Procedure Related - Once updating library by admin/update_library, once you open the select box for Procedures, we still see some "My New Procedures" in the list. These procedures are not completed but they are active on database. This box should be populated with procedures "complete" and "active" and owner = "12" (admin). | Glitch | Gateway |  | 30mins | Dec-14-2015 |  | Dec-17-2015 | Glitch | Done
253 | New Library - Procedure Related - dev side Once tryed to insert new library, system brings error into the select box for procedures. | Glitch | Gateway |  | 30mins | Dec-14-2015 |  | Dec-17-2015 |  | Done
254 | DROT - Purchase As employer, selected one DROT, clicked "Buy DROT", modal comes but after clicked "buy it", system does not close modal. The process of purchase is done, I checked the inventory but had to refresh the page, the function is working properly, but we expect system close modal and update the inventory automatically. | Glitch | Gateway |  | 3 | Dec-14-2015 |  |  | Change Request |  | Dec-22-2015 [Kartik]: Provide Priority then I could plan timelines
255 | My Library - points not matching from s1library Hazards - system is not saving the right points into tbl_my_library, and showing wrong number of points on each tile into My Hazards page. See my last purchase item from tbl_my_library, done on mys1s.ca/s1dev. check the dbdevsafe database: SELECT * FROM `tbl_my_library` WHERE `id` = 1073 AND `user_id` = 20 AND `lib_id` = 332 SELECT * FROM `tbl_library` WHERE `library_id` = 332 | Glitch | Gateway |  | 30mins | Dec-14-2015 |  | Dec-17-2015 |  | Done
256 | Notification - Header menu - Settings section with notification "zero" - Logged as Union, if user has one notification for "Connection", once this section is currently on Profile-home and Profile-settings, the header displays rightly the notification (1) over the Home icon, but wrongly (0) over the Settings icon. | Glitch | Gateway |  | 2 | Dec-14-2015 |  | Dec-18-2015 | Not a Glitch | Done | Dec-18-2015 [Kartik]: I have check and reviewed my scripts prior to upload found that, "Profile Settings notification criteria" was only checked for the "New Hazards Alerts" and "New Safety talks Completed Alerts" and i.e for the Non-Employers and Non-Consultants users, So I have not checked the "Connections Alerts" for the Profile Settings notification criteria, Now I have checked the same and updated on the development server. | [Dec-17-2015] Kartik, it is still wrong, you have just hidden the notification "zero". For Union User with one new connection, the notification should appears with (1) over the profile home icon and settings icon, because this user has connection tile in both pages, you need to review the scripts and not only hide the "zeros".
257 | MY WORKERS page - Profile id Card is not being displayed, tested as s1employer, tryed to click over images of my workers and nothing happened, however a frontend javascript error was found once inspected item, as uncaught error, please check it. | Glitch | Gateway |  | 2 | Dec-17-2015 |  |  | Glitch |  | Dec-22-2015 [Kartik]: Provide Priority then I could plan timelines
258 | MY PROCEDURES - - Opened procedures from My H&s Program/My Procedures, but system is not showing contents under the sections. Tested with s1employer for s1 procedures. All data is already in the database, but not coming to show in the proper sections, check procedure 1d=140 and 112 for example. | Glitch | Gateway |  | 3 | Dec-17-2015 |  |  | Glitch |  | Dec-22-2015 [Kartik]: Provide Priority then I could plan timelines

## Tasks Schedule
Month-Year | Item No. | Item Type | Priority | Hours | Status | Gateway Analysis | Comments
2016-01-01
| 177 | Enhancement | 1 | 12 | In Progress | Enhancement | Please refer list of pages to be coverd in the "Dec-22-2015" column of "Item Comments" Tab, Let us know in case of anything, we could revise timeline provided.
| 14 | Glitch | 1 | 4 | Pending | Glitch
| 179 | Enhancement | 1 | 4 | In Progress | Enhancement | Please refer list of pages to be coverd in the "Dec-22-2015" column of "Item Comments" Tab, Let us know in case of anything, we could revise timeline provided.
| 173 | Enhancement | 2 | 20 | Not Started | Enhancement
| 34 | Enhancement | 3 | 16 | Not Started | Enhancement
| 49 | Gap | 3 | 7 | Not Started | Gap
| 19 | Enhancement | 3 | 6 | 90% Done(On Hold) | Enhancement
| 254 | Glitch | Yet not given | 3 | Not Started | Change Request
| 257 | Glitch | Yet not given | 2 | Not Started | Glitch
| 258 | Glitch | Yet not given | 3 | Not Started | Glitch
[6 empty] | Leave Dates | Type of Leave
[6 empty] | 2016-01-14 | Official leave
[6 empty] | 2016-01-15 | Personal leave
[6 empty] | 2016-01-26 | Official leave
[6 empty] | Delivery Date: | 03-Feb-16(Canada Time)

## Item Commets
Item No. | Gateway comments
| Dec-22-2015 | Dec-24-2015 | Dec-25-2015 | Dec-28-2015
179 | Timeline of 12hrs after the new files/directory structure received. 30hrs timeline was for the old structure received before Dec-10-2015. Timelines and Estimated delivery specied by considering the current files and directory structure. Pages considered for the Estimated delivery date are: union/union-detail.php, union/courses.php, union/courses-detail.php | Except following points, "Item#179 - UNION DATA COLLECTION - implement scripts", has been uploaded on development server. i) Common search filter on right top corner ii) Pending because, On the courses.php, "Location" wise filter in Courses Grid, is newly added feature as It was not available in the version which I received on 10Dec2015, So Kindly explain this feature | 1. Please find attached screenshot unioncourse1.png: --> in this image you can see one library type "Liuna - Health & Safety" title "Propane - IW030" id=170, this piece of library is an Union Course active, which we differentiated as special library type. [Kartik] - As per my status email of yesterday, courses and courses details pages are uploaded on development server. 2. Find attached screenshot unioncourse2.png: --> in this image you can see active Unions, specially Local 183 (id=135) and LiUNA! Local183 (Training centre for Local183, id=181). [Kartik] - As per my status email of yesterday, courses and courses details pages are uploaded on development server. 3. Find attached screenshot unioncourse3.png: --> in this image you can see all three library types related to union and their parents: Local183 (id=135) and LiUNALocal183(Training centre for Local183, id=181), therefore these Unions share same library which is Union Course. I have no idea why you haven't saved them into table "tbl_union_courses" however I'm extremely sure this relationship should be considered accordingly. [Kartik] - In the table "tbl_union_courses", I am storing those courses which are Activated and Started by users from the "Instructor Portal" page, So there is no point to store Unions which we update "parent_library_type" within the table "tbl_library_types". | 1. Once I'm logged as Local183(id=135), if I access my public page (http://mys1s.ca/s1dev/admin/s1_public_page_union?id=135), once hit button "Go" under "My Data Collection" section, we should access the page: http://mys1s.ca/s1dev/admin/union_datacollection? id=135&design=1, however system opens page http://mys1s.ca/s1dev/admin/union_datacollection with no information. [Kartik] Dec-28-2015: Because I found this line $url = $base."admin/union_datacollection?id=".$union['id'] is replaced with replaced $url = $base."admin/union_datacollection";, So How could system recognize the user id if "union id" from the url removed ? This has been updated now. 2. On http://mys1s.ca/s1dev/admin/union_datacollection?id=135&design=1, although this union has 21 connections, 20 of them with English as their preferred language, the chart for languages has not been displayed. [Kartik] Dec-28-2015: In the GRID, I displayed "preferred language" from the "tbl_usermeta" table where preferred_language is not available for all users same as for Language Chart, So I am showing "N/A" who doesn't have "preferred_lanaguage" to get exact result in percentage. 3. Under table "USERS", columns "H&S Rep", "Union Rep" and "JHSC" should not be clickable, it should be populated with or without checkmark from information coming from database, this is only a view without edit function. [Kartik] Dec-28-2015: Actually, I understood and implemented as per your comments "H&S REP, UNION REP and JHSC, please insert "checkmark" icon, once required", So I kept checkmark icon in all users, However I changed it now as per the more detailed explanation. 4. Filter is still not working; [Kartik] Dec-28-2015: This is pending. Repeating Again that as per my comments in emails on 24Dec and 25Dec, "This is a common function of Union and Admin data collection pages, So It’s not even implemented as per my status email on Union Data Collection yesterday." 5. Under Courses page, the number of connections on section "Public Page" were changed from 21 to 22 connections, it should be same information previously displayed on the main page. [Kartik] Dec-28-2015: Previously, I had considered the connections of Selected Union's Courses, So System was showing different figure, However I had updated with the same as main union page as per your comments here. 6. Under Courses page, "COURSES" table, if we have "0" on column #students, "0%" on column Attendance, and "empty" on column Instructor, how do we have 0.04% of Average Score and 75% of Passing Score? These scores should be related to the Date the course was presented(activated from one Instructor and opened from one attendance). [Kartik] Dec-28-2015: Verification in Progress, I would check tomorrow on 29Dec2015. 7. Under courses page, "COURSES" table, if we have on column "Prefer.Language" English, it means the majority of attendance had English as their preferred language, how we have 100% of Portuguese in the "Languages" chart? [Kartik] Dec-28-2015: As per your comments in Requirement specification: "10.6.5. Prefer. Language is the second language of each user who attended the course;", In the Language Chart, I previously displayed "second_language" from the "tbl_usermeta" table where second_language is not available for all users, That's why I am showing "N/A" who doesn't have "second_language", to get exact result in percentage. Hence Now I made changes as per comments here, and displaying "preferred_language" only and showing "N/A" wherever required. In the Courses GRID, I am showing language of the Courses displayed.
177 | Timeline of 20hrs after the new files/directory structure received. 44hrs timeline was for the old structure received before Dec-10-2015. Timelines and Estimated delivery specied by considering the current files and directory structure. Pages considered for the Estimated delivery date are: admin/union.php, admin/union-detail.php, admin/consultants.php, admin/consultants-detail.php, admin/consultants-courses.php, admin/consultants-courses-detail.php, admin/purchases.php, admin/due-diligence.php, admin/user.php. In Other pages HTML looks not completed, let me know which other pages need to cover so I could provide updated Estimated Date and Timelines |  | [Kartik] - First of all, I have not mentioned any updates in my status email of yesterday, and as per the recent Task Sheet shared, I had mentioned Estimated Date: 28Dec2015(CST) for the Admin Data Collection module after revised functionality by considering the time I spent for the files & directory structures changes in pages I received on 10Dec2015. -> Although, As per your review, I checked the Purchases Page of Admin Data Collection and so find my comments in GREEN stated below: ------------------------------------------------------------------------------------------------------------- 1. Filter is not working; [Kartik] – This is a common function of Union and Admin data collection pages, So It’s not even implemented as per my status email on Union Data Collection yesterday. 2. Printing button is not working 100%, it opens new page with the elements to be choose to print but does not trigger the actual Printer. [Kartik] - Done 3. for the first line of totals for Gold, Silver and Bronze packages: 3.1. Gold total is right; [Kartik] - Ok 3.2. Total of Silver sold, as per the scripts on dev database should be 40000, not 15000, please see scripts below and double check it: --> this first script shows the users and their purchases SELECT id, in_user_id, in_credits_purchased, in_qty_ordered , (in_credits_purchased*in_qty_ordered) as total FROM `tbl_my_credits` where st_credits_package = "Silver" and in_user_id not in (9,12) ORDER BY `in_user_id` DESC --> this second one shows the total of each user and total general amount. SELECT id, in_user_id, sum(in_credits_purchased*in_qty_ordered) as total FROM `tbl_my_credits` where st_credits_package = "Silver" and in_user_id not in (9,12) Group BY `in_user_id` with rollup [Kartik] – I was showing highest figure on this tiles, though it’s been changed now. Why you have mention “in_user_id not in (9,12)” ? 3.3 Total of Bronze also doesn't look right, it should show 27500 not 5000, please see scripts below: --> this first script shows the users and their purchases SELECT id, in_user_id, in_credits_purchased,in_qty_ordered, (in_credits_purchased*in_qty_ordered) as total FROM `tbl_my_credits` where st_credits_package = "Bronze" and in_user_id not in (9,12) ORDER BY `in_user_id` DESC --> this second one shows the total of each user and total general amount. SELECT id, in_user_id, sum(in_credits_purchased*in_qty_ordered) as total FROM `tbl_my_credits` where st_credits_package = "bronze" and in_user_id not in (9,12) Group BY `in_user_id` with rollup [Kartik] – I was showing highest figure on this tiles, though it’s been changed now. Why you have mention “in_user_id not in (9,12)” ? 4. For the second line of totals for Credits, Purchases and Points: 4.1. Credits total is wrong, for S1 Employer (user id=20) you are considering only "my credits"- "my libray purchased by credits", but you should also include the credits assigned from admin, see scripts below: --> if you run sql below, you will find user 20 has bought 50000 credits SELECT in_user_id, sum(in_credits_purchased*in_qty_ordered) as total FROM `tbl_my_credits` group by in_user_id ORDER BY total DESC --> if you run sql below, you will find user 20 has spent 2495 credits in library purchases: SELECT user_id, sum(creditsbuy) as total FROM `tbl_my_library` WHERE transaction_type = 's1credits' group by user_id order by total desc --> if you run sql below, you will find user 20 has received by assignment from admin 20300: SELECT in_credits_assign_to, sum(in_credits_assigned) as total FROM `tbl_credits_assign` where st_credits_assign_status = 'assigned' group by in_credits_assign_to --> if you run sql below, you will find user 20 has requested 10000 points: SELECT * FROM `tbl_credits_requests` where st_credits_requested_by = 's1employer@hrqsolutions.com' and st_credits_request_status = 'approved' --> The conclusion is: user 20(s1 employer) should have 50000 - 2495 + 20300 + 10000 = 77805, not 47505 as displayed on this section and on the Header menu bar. [Kartik] – I had not included Credits spent on purchases and Credits approved by Admin, Which has been added now. 4.2. Purchases total is wrong: --> if you run sql below you will find user s1employer(id=20) has spent 13799.05 buying libraries: SELECT user_id, sum(unit_price) as total FROM `tbl_my_library` WHERE transaction_type = 'moneris' group by user_id order by total desc --> if you run sql below you will find user s1employer has spent 5650 buying credits: SELECT in_user_id, sum(in_credits_price*in_qty_ordered) as total FROM `tbl_my_credits` group by in_user_id ORDER BY total DESC --> if you run sql below you will find user s1employer has spent 1211 by credits assigned by admin: SELECT in_credits_assign_to, sum(in_credits_price) as total FROM `tbl_credits_assign` where st_credits_assign_status = 'assigned' group by in_credits_assign_to --> if you run sql below you will find user s1employer has spent 3501 requesting credits(double check if once user request credits, you are inserting it or not into table tbl_my_library, if yes we should not take this table for this formula) SELECT * FROM `tbl_credits_requests` where st_credits_requested_by = 's1employer@hrqsolutions.com' and st_credits_request_status = 'approved' --> CONCLUSION: s1employer has spent 13799.05 + 5650 + 1211 = 20660.05, however if the last amount of 3501 was not already included on tbl_my_library, this total goes to 20660.05 + 3501 = 24161.05 I believe it is already inserted, but you should check if it the system is still inserting it there in these cases. [Kartik] – As per the LABEL “Purchases” suggests, I believe the Amount of Credits which were assigned to user and requested by user, should not be the part of this “Purchases” tile. Though I included Amount of Credits from the “tbl_my_credits” table now. Kindly share your thoughts. 4.3. Points total is under investigation: it looks wrong, however I can't assume that due to a number of tables regarding points. Please let me know how do you do it. --> if you run sql below you will find user s1employer has 515 points: SELECT in_user_id, sum(in_credits) as total FROM `tbl_points_of_users` group by in_user_id ORDER BY total DESC --> if you run sql below you will find user s1employer has 0 points, and the winner of more points would be user id=283 with 215 points: SELECT in_user_id, sum(in_total_points_gained) as total FROM `tbl_users_points_level` group by `in_user_id` order by total desc --> if you run sql below you will find user s1employer has 15 points SELECT m.user_id, sum(p.in_credits) as points FROM `tbl_user_pagepoints` m, `tbl_point_page_sections` p where m.page_id = p.in_page_id and m.point_id = p.in_pointpage_section_id group by m.user_id order by points desc --> CONCLUSION: for this element(total of points), please check where the system is saving the points, create sql and send to me in order to double check it further more. [Kartik] – The table ‘tbl_user_pagepoints’ is not in use any more. And I am using function getS1Points() which is exists in points modal. 5. Table SIMPLE TABLE: 5.1. Rename "Simple Table" to "Users" [Kartik] – Requested changes has been incorporated. 5.2. Do not show users with Zero in all three columns: Purchases, Points and Credits. [Kartik] – Requested changes has been incorporated. 6. PURCHASES chart: 6.1. For purchases line: check these amounts based in all tables I have mentioned in the item 4.2. above; [Kartik] – Verification in Progress 6.2. For points line: check these amounts based in all tables I have mentioned in the item 4.3. above; [Kartik] – Verification in Progress

## Summary(old)
If you want to count then kindly do those which are stated in Bold
Items type | Gateway Analysis | No. of Items | No. of Hours
Total |  | 71 | 287
Mentioned as Enhancements |  | 30 | 171
Mentioned as Glitches |  | 35 | 93
| Actual Glitches | 15 | 43
| Actually it's CR / Working fine / Design related issue / Repeated | 20 | 50
Mentioned as Review |  | 2 | 6
Mentioned as Incomplete |  | 2 | 7
Total mentioned as Gap |  | 2 | 10
| Actually it's CR | 2 | 10
Subject | No. of Hours
Total Hours of Actual Glitches as per Gateway Analysis: | 43
Total Hours of Items which are not glitches as per Gateway Analysis | 50

## WSIB-RateGroup
Sector | Rate Group | Description
Agriculture | 159 | Livestock Farms
Agriculture | 167 | Field Crop, Fruit And Vegetable Farms
Agriculture | 174 | Tobacco And Mushroom Farms
Agriculture | 181 | Fishing And Miscellaneous Farming
Agriculture | 184 | Poultry Farms And Agricultural Services
Agriculture | 190 | Landscaping And Related Services
Automotive | 419 | Motor Vehicle Assembly
Automotive | 420 | Motor Vehicle Engine Manufacturing
Automotive | 421 | Other Motor Vehicle Parts And Equipment
Automotive | 424 | Motor Vehicle Stampings
Automotive | 425 | Motor Vehicle Wheels And Brakes
Automotive | 428 | Motor Vehicle Fabric Accessories
Automotive | 432 | Trucks, Buses And Trailers
Construction | 704 | Electrical And Incidental Construction Services
Construction | 707 | Mechanical And Sheet Metal Work
Construction | 711 | Roadbuilding And Excavating
Construction | 719 | Inside Finishing
Construction | 723 | Industrial, Commercial & Institutional Construction
Construction | 728 | Roofing
Construction | 732 | Heavy Civil Construction
Construction | 737 | Millwrighting And Welding
Construction | 741 | Masonry
Construction | 748 | Form Work And Demolition
Construction | 751 | Siding And Outside Finishing
Construction | 755 | Non-Exempt Partners and Executive Officers in Construction
Construction | 764 | Homebuilding
Education | 810 | School Boards
Education | 817 | Educational Facilities
Electrical | 830 | Power And Telecommunication Lines
Electrical | 833 | Electric Power Generation
Electrical | 835 | Oil, Power And Water Distribution
Electrical | 983 | Communications Industries
Food | 207 | Meat And Fish Products
Food | 210 | Poultry Products
Food | 214 | Fruit And Vegetable Products
Food | 216 | Dairy Products
Food | 220 | Other Bakery Products
Food | 222 | Confectionery
Food | 223 | Biscuits, Snack Foods And Other Food Products
Food | 226 | Crushed And Ground Foods
Food | 230 | Alcoholic Beverages
Food | 231 | Soft Drinks
Forestry | 30 | Logging
Forestry | 33 | Mill Products And Forestry Services
Forestry | 36 | Veneers, Plywood And Wood Preservation
Health Care | 851 | Homes For Nursing Care
Health Care | 852 | Homes For Residential Care
Health Care | 853 | Hospitals
Health Care | 857 | Nursing Services
Health Care | 858 | Group Homes
Health Care | 861 | Treatment Clinics And Specialized Services
Health Care | 875 | Professional Offices And Agencies
Manufacturing | 238 | Other Rubber Products
Manufacturing | 289 | Cloth, Carpets And Textile Products
Manufacturing | 301 | Clothing, Fibre And Yarn
Manufacturing | 308 | Millwork And Other Wood Industries
Manufacturing | 311 | Wooden Cabinets
Manufacturing | 312 | Wooden Boxes And Pallets
Manufacturing | 322 | Upholstered Furniture
Manufacturing | 323 | Metal Furniture
Manufacturing | 325 | Wooden And Other Non-Metal Furniture
Manufacturing | 328 | Furniture Parts And Fixtures
Manufacturing | 333 | Printing, Platemaking And Binding
Manufacturing | 335 | Publishing
Manufacturing | 338 | Folding Cartons
Manufacturing | 341 | Paper Products
Manufacturing | 374 | Doors And Windows
Manufacturing | 375 | Structural And Architectural Products
Manufacturing | 377 | Coating Of Metal Products
Manufacturing | 379 | Hardware, Tools And Cutlery
Manufacturing | 382 | Metal Dies, Moulds And Patterns
Manufacturing | 383 | Heating, Refrigeration And Air Conditioning Equipment
Manufacturing | 385 | Machine Shops
Manufacturing | 387 | Other Metal Fabricating Industries
Manufacturing | 389 | Metal Closures And Containers
Manufacturing | 390 | Other Stamped And Pressed Metal Products
Manufacturing | 393 | Wire Products
Manufacturing | 402 | Major Appliances And Transmission Equipment
Manufacturing | 403 | Other Machinery And Equipment
Manufacturing | 406 | Elevators And Escalators
Manufacturing | 408 | Boilers, Pumps And Fans
Manufacturing | 411 | Agricultural, Construction And Mining Machinery
Manufacturing | 417 | Aircraft Manufacturing
Manufacturing | 442 | Railroad Rolling Stock
Manufacturing | 460 | Lighting And Small Electrical Appliances
Manufacturing | 466 | Communication And Energy Wire Products
Manufacturing | 468 | Electronic Equipment & Other Communication Devices
Manufacturing | 477 | Industrial Electrical Equipment
Manufacturing | 485 | Bricks, Ceramics And Abrasives
Manufacturing | 496 | Concrete Products
Manufacturing | 501 | Non-Metallic Mineral Products
Manufacturing | 502 | Glass Products
Manufacturing | 529 | Jewelry And Instruments
Manufacturing | 533 | Signs And Displays
Manufacturing | 538 | Sporting Goods And Toys
Manufacturing | 542 | Other Manufactured Products
Manufacturing | 612 | Agricultural Products, Sales
Manufacturing | 670 | Machinery And Other Vehicles, Sales
Manufacturing | 685 | Metal Products, Wholesale
Manufacturing | 838 | Natural Gas Distribution
Manufacturing | 905 | Apartment And Condominium Services
Manufacturing | 908 | Other Real Estate Services
Manufacturing | 911 | Security And Investigation Services
Manufacturing | 923 | Janitorial Services
Manufacturing | 958 | Technical And Business Services
Manufacturing | 975 | Linen And Laundry Services
Mining | 110 | Gold Mines
Mining | 113 | Nickel Mines
Mining | 119 | Other Mines
Mining | 134 | Aggregates
Municipal | 845 | Local Government Services
Primary Metals | 352 | Steel And Other Smelting And Refining Industries
Primary Metals | 358 | Foundries
Primary Metals | 361 | Non-Ferrous Metal Industries
Process / Chemicals | 258 | Foamed And Expanded Plastic Products
Process / Chemicals | 261 | Plastic Film And Sheeting
Process / Chemicals | 263 | Other Plastic Products
Process / Chemicals | 507 | Petroleum And Coal Products
Process / Chemicals | 512 | Resins, Paint, Ink And Adhesives
Process / Chemicals | 514 | Pharmaceuticals And Medicines
Process / Chemicals | 517 | Soap And Toiletries
Process / Chemicals | 524 | Chemical Industries
Pulp & Paper | 39 | Pulp, Newsprint And Specialty Papers
Pulp & Paper | 41 | Corrugated Boxes
Services | 604 | Food, Sales
Services | 606 | Grocery And Convenience Stores
Services | 607 | Specialty Food Stores
Services | 608 | Beer Stores
Services | 630 | Vehicle Services And Repairs
Services | 633 | Petroleum Products, Sales
Services | 636 | Other Sales
Services | 638 | Pharmacies
Services | 641 | Clothing Stores
Services | 657 | Automobile And Truck Dealers
Services | 668 | Computer, Electronic And Electrical Equipment, Sales
Services | 919 | Restaurants And Catering
Services | 921 | Hotels, Motels And Camping
Services | 929 | Supply Of Non-Clerical Labour
Services | 933 | Equipment Rental And Repair Services
Services | 937 | Recreational Services And Facilities
Services | 944 | Personal Services
Services | 956 | Legal And Financial Services
Services | 962 | Advertising And Entertainment
Services | 981 | Membership Organizations
Transportation | 497 | Ready-Mix Concrete
Transportation | 551 | Air Transport Industries
Transportation | 553 | Air Transport Services
Transportation | 560 | Warehousing
Transportation | 570 | General Trucking
Transportation | 577 | Courier Services
Transportation | 580 | Miscellaneous Transport Industries
Transportation | 584 | School Buses
Transportation | 590 | Ambulance Services
Transportation | 681 | Lumber And Builders Supply
Transportation | 689 | Waste Materials Recycling